# Decision Artifact Set

### October 2026 · Value Lattice

Three records that keep a purchase decision in view after the contract is signed. The Decision Memo is written when the commitment is made. The Executive Readout is produced on a fixed cadence while the work is underway. The Audit Record is written when realization is complete. All three share one outcome table, so the numbers a buyer commits to are the same numbers the readouts report and the audit checks.

| File | What it is | When it is written | Who writes it |
| --- | --- | --- | --- |
| Decision Memo | The record of what was decided: outcomes, metrics, baselines, targets, assumptions and the conditions on each side. | At commitment, before signature. | The business owner, with Finance. |
| Executive Readout | Where each committed outcome stands against plan, which assumptions still hold, and what the decision authority needs to act on. | On the governance cadence, usually monthly or quarterly. | The business owner. The vendor supplies data it holds. |
| Audit Record | Expected against actual for every outcome, the variance and its cause, and the lessons written as changes to the next decision. | At the close of realization. | The business owner, reviewed by Finance. |
| Worked Example | A completed set for a fictional distribution company, from memo to audit. | Read it first. |  |
| Decision Artifact Workbook | The same three records on linked sheets. Planned progress, status, variance and the verdict are calculated. | Alongside the Word files, or instead of them. |  |

Free. No sign-up, no email address, no registration. Licensed CC BY 4.0: use it, change it, put your own name on it, issue it inside your company or to your suppliers. Keep the attribution line so the next reader can find the latest copy.

Start here. Read the worked example, then open the Decision Memo template for a purchase you are about to sign.

## Where the set fits

The other guides on the same page cover the steps before and around these three.

- Request for Value, before the market is asked: what the purchase has to produce, measured how.

- The Verification Line, in the contract: how the buyer will know the value arrived, and what follows if it does not.

- Decision Memo, at commitment: the outcomes and metrics from the RFV, carried forward unchanged, with the assumptions the decision rests on.

- Executive Readout, during execution: the same outcomes, reported against plan on a fixed cadence.

- Audit Record, at verification: what was committed, what arrived, and what the next decision should do differently.

The Purchase Outcome Register holds every significant purchase in one place for the CFO and the board. A completed Audit Record is the closing entry for that purchase’s row.

## Six rules built in

- One outcome table. An outcome ID set in the memo is used unchanged in every readout and in the audit. If a metric or target has to change, the change is recorded with its date, reason and approving body, and the original stays visible.

- Baselines come from the buyer’s own records, whoever proposes how to measure them. An outcome with no baseline yet is written down as such, and the first readout establishes it.

- Every assumption gets a test and a check date. The readout reports each one as holding, under pressure, or failed.

- Outcomes are held by roles, not by named people. The record has to survive a reorganization or a departure.

- A readout reports how the decision is performing, not what the project did. Milestones and activity belong in the project plan.

- Lessons are written as changes. Each lesson in the audit names what the next memo, RFV or contract will do differently.

## What a vendor that delivers gets from this

A result recorded by the buyer, against a baseline the buyer set, is the strongest reference a vendor can have. The Audit Record also states whose conditions held and whose did not, so a vendor is not blamed for a shortfall that came from the buyer’s side.

Published October 2026. Check valuelattice.com/guides/ for the latest copy before you issue one.

From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

# Worked Example: Meridian Logistics

### A completed Decision Artifact Set, from memo to audit · October 2026

Part of the Decision Artifact Set. Free to use, copy, adapt and issue. Published by Value Lattice · valuelattice.com/guides/ · Licensed CC BY 4.0

Meridian Logistics is a fictional distribution company, and every figure here is illustrative. The example follows the one used in The Value Standard. It shows how one outcome table carries from the memo, through a readout at month three, to the audit at month eighteen.

## Decision Memo (extract)

What was decided. Meridian will replace its order processing and warehouse management systems across its distribution centers, to shorten fulfillment, raise inventory accuracy and cut manual work in order handling.

| ID | Outcome | Metric | Baseline | Target | Target date | Owning role | Escalation threshold |
| --- | --- | --- | --- | --- | --- | --- | --- |
| O1 | Orders reach customers faster | Average fulfillment cycle time, days | 4.2 | 2.8 | Month 9 | VP Distribution Operations | More than 20% behind planned progress |
| O2 | Stock records match the shelves | Inventory accuracy, all distribution centers | 90% | 95% | Month 12 | VP Distribution Operations | More than 20% behind planned progress |
| O3 | The investment pays back | Month cumulative benefit first exceeds cumulative cost | Not applicable | Month 18 or sooner | Month 18 | Finance partner, Operations | Forecast later than month 18 |
| O4 | Less manual handling of orders | Reduction in orders needing manual intervention | 0% | 60% | Month 6 | Director, Order Management | More than 20% behind planned progress |

The baseline for O2 is illustrative and is not taken from the book.

| ID | Assumption | Depends on | How it will be tested | Check date |
| --- | --- | --- | --- | --- |
| A1 | Staffing at each distribution center stays at planned levels through month 12 | Buyer | Headcount against plan, each readout | Every readout |
| A2 | The legacy warehouse system integration is complete on schedule | Both | Integration acceptance sign-off | Month 4 |
| A3 | Migrated stock records meet the agreed data quality threshold before each center goes live | Both | Sample audit of migrated records before cutover | Before each cutover |

## Executive Readout, month 3

| ID | Planned at month 3 | Actual | Status | Note |
| --- | --- | --- | --- | --- |
| O1 | 3.73 days | 3.1 days | On plan | Ahead of the straight line, not yet at target |
| O2 | 91.25% | 91% | Behind | Data migration issue at one center |
| O3 | Breakeven by month 18 | Forecast month 18 | On plan |  |
| O4 | 30% | 38% | On plan | Ahead of the six-month trajectory |

| ID | Assumption | Status | Effect |
| --- | --- | --- | --- |
| A1 | Staffing | Holding | None |
| A2 | Integration | Holding | None |
| A3 | Data migration quality | Partly failed | Holds O2 back |

Correction recorded. Record cleanup was added before the remaining centers move over. The O2 target and date were left unchanged, and the change was entered in the memo’s change table with the steering committee’s approval.

## Audit Record, month 18

| ID | Committed | Actual | Variance | Verdict |
| --- | --- | --- | --- | --- |
| O1 | 2.8 days by month 9 | 2.6 days | 0.2 days better than target | Met |
| O2 | 95% by month 12 | 94.2% | 0.8 points short | Partly met |
| O3 | Breakeven by month 18 | Month 16 | Two months early | Met |
| O4 | 60% by month 6 | 67% | 7 points better than target | Met |

Cause of the O2 variance. One distribution center was added partway through the program with a compressed onboarding timeline. That is a buyer-side condition. It was not in the memo as an assumption, and it first showed up in the readouts as the A3 data quality problem.

| Lesson | Change to apply | Where it goes |
| --- | --- | --- |
| Data migration quality has to be checked before a center goes live, not after | A pre-cutover data quality test becomes a standing assumption with its own check date | Next Decision Memo, section 3 |
| A center added mid-program cannot meet the same accuracy date as the others | A center added after commitment gets its own target and date, recorded as a change | Next Decision Memo, sections 2 and 8 |

These lessons go into Meridian’s next major technology decision.

## What the example shows

The memo set four outcomes with baselines and dates. The month-three readout caught the data problem early and recorded the fix without moving the target. The audit then separated a shortfall caused on the buyer’s side from the vendor’s delivery, so the vendor’s record shows its own conditions met.

From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

# Decision Memo

### The record of what was decided · Template · October 2026

Part of the Decision Artifact Set. Free to use, copy, adapt and issue. Published by Value Lattice · valuelattice.com/guides/ · Licensed CC BY 4.0

Write this when the decision is made and before the contract is signed. It records what the organization committed to, in terms specific enough to check later. Every readout and the final audit work from this page, so the numbers here are the ones that count.

## Header

| Field | Entry |
| --- | --- |
| Decision |  |
| Date decided |  |
| Decision authority (the body or role that approved it) |  |
| Business owner (role) |  |
| Finance partner (role) |  |
| Vendor or vendors |  |
| Contract reference |  |
| Request for Value reference, if one was issued |  |
| Memo version and date |  |

## 1. What was decided

Two or three sentences: what is being bought, from whom, to produce what, at what committed cost, over what period.

## 2. Committed outcomes

One row per outcome. Use the outcome IDs (O1, O2 and so on) in every readout and in the audit. If you issued a Request for Value, the outcomes and metrics come from it unchanged.

| ID | Outcome, in the business owner’s words | Metric | Baseline (value, date, source) | Target | Target date |
| --- | --- | --- | --- | --- | --- |
| O1 |  |  |  |  |  |
| O2 |  |  |  |  |  |
| O3 |  |  |  |  |  |
| O4 |  |  |  |  |  |

How each outcome is measured and governed:

| ID | How it is measured | Data source | Owning role | Reporting cadence | Escalation threshold |
| --- | --- | --- | --- | --- | --- |
| O1 |  |  |  |  |  |
| O2 |  |  |  |  |  |
| O3 |  |  |  |  |  |
| O4 |  |  |  |  |  |

Notes for these tables. The baseline comes from your own records. If there is no baseline yet, write “to be established” and name the readout that will establish it. The escalation threshold says how far behind plan an outcome can fall before the decision authority must act, for example “more than 20 percent behind planned progress at any readout.”

## 3. Assumptions

The things that must stay true for the outcomes to be reachable. Each one gets a test and a date.

| ID | Assumption | Outcomes that depend on it | Depends on (buyer, vendor, both, external) | How it will be tested | Check date | If it fails |
| --- | --- | --- | --- | --- | --- | --- |
| A1 |  |  |  |  |  |  |
| A2 |  |  |  |  |  |  |
| A3 |  |  |  |  |  |  |

## 4. Conditions on each side

What each party must have in place. A shortfall later is judged against these.

| Buyer-side conditions | Vendor-side conditions |
| --- | --- |

## 5. Committed cost

| Item | Amount | Period |
| --- | --- | --- |
| One-time cost |  |  |
| Recurring cost |  |  |
| Internal effort (people, time) |  |  |
| Total committed |  |  |

## 6. Governance cadence

| Field | Entry |
| --- | --- |
| Readout frequency |  |
| Readout goes to (decision authority) |  |
| Escalation route |  |
| First readout date |  |
| Audit Record due date |  |
| Where this memo is filed |  |

## 7. Alternatives considered

| Alternative | Why it was not chosen |
| --- | --- |
| Do nothing |  |

## 8. Approval and changes

| Field | Entry |
| --- | --- |
| Approved by (decision authority) |  |
| Date |  |

Changes after approval. A change to an outcome, metric, baseline or target is recorded here. The original stays in section 2 and is not overwritten.

| Date | Outcome ID | What changed | Why | Approved by |
| --- | --- | --- | --- | --- |

## Before you call it final

- ☐ Every outcome has a metric, a baseline (or a named readout that will set it), a target and a date.

- ☐ Every metric is worded the same way here, in the RFV and in the contract.

- ☐ Every assumption has a test and a check date.

- ☐ Every outcome is held by a role, not a named person.

- ☐ The first readout date and the audit date are set.

From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

# Executive Readout

### How the decision is performing · Template · October 2026

Part of the Decision Artifact Set. Free to use, copy, adapt and issue. Published by Value Lattice · valuelattice.com/guides/ · Licensed CC BY 4.0

Produce this on the cadence set in the Decision Memo. It reports whether the committed outcomes are arriving, whether the assumptions behind them still hold, and what the decision authority needs to decide. Project activity and milestones belong in the project plan. Two pages is enough.

## Header

| Field | Entry |
| --- | --- |
| Decision |  |
| Decision Memo version used |  |
| Readout number |  |
| Period covered |  |
| Months since commitment |  |
| Prepared by (role) |  |
| Goes to (decision authority) |  |
| Date |  |

## 1. Summary

| Question | Answer |
| --- | --- |
| Outcomes on plan or ahead |  |
| Outcomes behind or at the escalation threshold |  |
| Assumptions under pressure or failed |  |
| Does the decision authority need to act? If so, on what? |  |

## 2. Outcome performance

Planned value is where the outcome should be at this point if it moves in a straight line from the baseline to the target. Status compares actual progress with planned progress. The workbook calculates both.

| ID | Metric | Baseline | Target and date | Planned at this point | Actual | Status | Source of the actual | Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| O1 |  |  |  |  |  |  |  |  |
| O2 |  |  |  |  |  |  |  |  |
| O3 |  |  |  |  |  |  |  |  |
| O4 |  |  |  |  |  |  |  |  |

Status values. Target reached · On plan · Behind (short of planned progress, inside the threshold) · Escalate (past the threshold set in the memo).

## 3. Assumptions

| ID | Assumption | Status (holding, under pressure, failed) | Evidence | Effect on outcomes |
| --- | --- | --- | --- | --- |
| A1 |  |  |  |  |
| A2 |  |  |  |  |
| A3 |  |  |  |  |

## 4. Emerging risks

| Risk | Outcomes affected | How likely | Proposed response |
| --- | --- | --- | --- |

## 5. Corrections made this period

A correction to a target or metric is also recorded in the memo’s change table. The original target stays visible in both places.

| What was changed | Why | Approved by | Effect on targets |
| --- | --- | --- | --- |

## 6. Decisions requested

| Decision needed | Options | Recommendation | Needed by |
| --- | --- | --- | --- |

From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

# Audit Record

### What was committed, what arrived, and what changes next time · Template · October 2026

Part of the Decision Artifact Set. Free to use, copy, adapt and issue. Published by Value Lattice · valuelattice.com/guides/ · Licensed CC BY 4.0

Write this when realization is complete, against the Decision Memo that was approved, including any recorded changes. It is a permanent record. Its last section feeds the next decision.

## Header

| Field | Entry |
| --- | --- |
| Decision |  |
| Decision Memo version used as the baseline |  |
| Realization period |  |
| Audit date |  |
| Prepared by (role) |  |
| Reviewed by (Finance role) |  |
| Purchase Outcome Register row, if kept |  |

## 1. Outcomes: committed against actual

| ID | Metric | Baseline | Committed target and date | Actual and date measured | Variance | Verdict (met, partly met, not met) | Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- |
| O1 |  |  |  |  |  |  |  |
| O2 |  |  |  |  |  |  |  |
| O3 |  |  |  |  |  |  |  |
| O4 |  |  |  |  |  |  |  |

Verdict rule used in the workbook. Met: the full planned change arrived. Partly met: at least half of it arrived. Not met: less than half. Adjust the rule if your organization uses another one, and say so here.

## 2. Causes of variance

| ID | Cause | Whose condition (buyer, vendor, both, external) | Was it named as an assumption in the memo? | First visible in readout number |
| --- | --- | --- | --- | --- |

## 3. Assumptions: how they held

| ID | Assumption | Held, partly held, or failed | When the readouts first showed it | What was done |
| --- | --- | --- | --- | --- |
| A1 |  |  |  |  |
| A2 |  |  |  |  |
| A3 |  |  |  |  |

## 4. Cost: committed against actual

| Item | Committed | Actual | Variance | Reason |
| --- | --- | --- | --- | --- |
| One-time cost |  |  |  |  |
| Recurring cost |  |  |  |  |
| Internal effort |  |  |  |  |

## 5. Lessons, written as changes

Each lesson names what the next decision will do differently and where that change goes.

| Lesson | Change to apply | Where it goes (next memo’s assumptions, RFV evidence requirements, contract terms, vendor evaluation) |
| --- | --- | --- |

## 6. Vendor record

What the vendor delivered against its own conditions, stated plainly. A future evaluation can rely on a result the buyer verified.

| Vendor condition | Met? | Note |
| --- | --- | --- |

## 7. Sign-off

| Field | Entry |
| --- | --- |
| Signed off by |  |
| Date |  |
| Filed at |  |

From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.