## Start Here
Decision Artifact Workbook
October 2026 · Value Lattice · Licensed CC BY 4.0
Three linked records for one purchase decision: the Decision Memo (at commitment), the Executive Readout (on a fixed cadence during execution) and the Audit Record (at the close of realization).
The workbook opens with a worked example for Meridian Logistics, a fictional distribution company. Every figure in it is illustrative. Replace the yellow cells with your own entries.
How the sheets work
Memo: one row per committed outcome. The outcome IDs, baselines and targets here feed every other sheet. Type is Trajectory (a number moving from baseline to target) or Milestone (a month by which something must happen, such as payback).
Assumptions: what must stay true for the outcomes to be reachable, each with a test, a check date and its latest status.
Readout: enter the months since commitment in cell B3 and the latest actual for each outcome. Planned value, progress and status are calculated.
Audit: enter the actual at the close of realization. Variance, share of the planned change achieved, and the verdict are calculated.
Lessons: each lesson written as a change to the next decision, and where that change goes.
Rules the calculations follow
Planned value assumes a straight line from the baseline to the target by the target month.
Status: Target reached when the full planned change has arrived. On plan when actual progress is at or ahead of planned progress. Behind when it is short but inside the escalation threshold set on the Memo sheet. Escalate when it is past that threshold. A Milestone is On plan when the forecast month is no later than the target month.
Verdict at audit: Met when the full planned change arrived, Partly met when at least half arrived, Not met otherwise. A Milestone is Met when it happened by the target month.
Baselines come from your own records. Outcomes are held by roles, not named people. If a target changes, record the change on the Memo sheet's change table and leave the original in place.
Free. No sign-up, no email address. Use it, change it, put your own name on it. Keep the attribution line below so the next reader can find the latest copy at valuelattice.com/guides/.
From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

## Memo
Decision Memo: committed outcomes
Written at commitment, before signature. Yellow cells are entries; the example is fictional.
Decision | Meridian Logistics: replace order processing and warehouse management systems across all distribution centers
Decision authority | Investment committee
Date decided | Month 0
ID | Outcome, in the business owner's words | Metric | Type | Unit | Baseline | Baseline date | Baseline source | Target | Target month | How it is measured | Data source | Owning role | Reporting cadence | Escalation threshold (share behind planned progress)
O1 | Orders reach customers faster | Average fulfillment cycle time | Trajectory | days | 4.2 | Month 0 | Order system, prior 6 months | 2.8 | 9 | Order release to delivery confirmation, monthly average | Order system | VP Distribution Operations | Monthly | 20%
O2 | Stock records match the shelves | Inventory accuracy, all distribution centers | Trajectory | % | 90 | Month 0 | Cycle counts (illustrative) | 95 | 12 | Cycle count matches against system record | Warehouse system | VP Distribution Operations | Monthly | 20%
O3 | The investment pays back | Month cumulative benefit first exceeds cumulative cost | Milestone | month |  |  |  | 18 | 18 | Finance tracking of benefit and cost | General ledger | Finance partner, Operations | Quarterly | 0%
O4 | Less manual handling of orders | Reduction in orders needing manual intervention | Trajectory | % | 0 | Month 0 | Order system exception log | 60 | 6 | Share of orders touched manually, against baseline | Order system | Director, Order Management | Monthly | 20%
Changes after approval (the original row above stays as it was)
Date | Outcome ID | What changed | Why | Approved by
Month 3 | O2 | Record cleanup added before remaining centers move over; target and date unchanged | Data migration quality partly failed (A3) | Steering committee
From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

## Assumptions
Decision Memo: assumptions
Each assumption gets a test and a check date. Status is updated at every readout.
ID | Assumption | Outcomes that depend on it | Depends on | How it will be tested | Check date | If it fails | Latest status | Evidence
A1 | Staffing at each distribution center stays at planned levels through month 12 | O1, O2, O4 | Buyer | Headcount against plan | Every readout | Re-sequence center cutovers | Holding | Headcount at plan in all centers
A2 | The legacy warehouse system integration is complete on schedule | O1, O2, O4 | Both | Integration acceptance sign-off | Month 4 | Hold further cutovers until accepted | Holding | Acceptance testing on schedule
A3 | Migrated stock records meet the agreed data quality threshold before each center goes live | O2 | Both | Sample audit of migrated records before cutover | Before each cutover | Clean records before cutover; report effect on O2 | Partly failed | One center below threshold at cutover
From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

## Readout
Executive Readout
Produced on the cadence set in the memo. Enter the months since commitment and the latest actuals.
Months since commitment | 3
ID | Metric | Type | Baseline | Target | Target month | Planned at this point | Actual (or forecast month for a Milestone) | Actual progress | Planned progress | Status | Source of the actual | Note
[7 empty] | 3.1 |  |  |  | Order system | Ahead of the straight line, not yet at target
[7 empty] | 91 |  |  |  | Cycle counts | Data migration issue at one center (A3)
[7 empty] | 18 |  |  |  | Finance forecast
[7 empty] | 38 |  |  |  | Exception log | Ahead of the six-month trajectory
Summary
On plan or target reached
Behind
Escalate
Assumptions under pressure or failed
Decision requested of the decision authority |  | None this period. Correction to A3 recorded on the Memo sheet.
From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

## Audit
Audit Record
Written at the close of realization, against the approved memo.
Audit at month | 18
ID | Metric | Type | Baseline | Committed target | Target month | Actual at audit (or month reached for a Milestone) | Variance against target | Share of planned change achieved | Verdict | Cause of variance | Whose condition | Evidence
[6 empty] | 2.6 | [5 empty] | Order system
[6 empty] | 94.2 |  |  |  | One center added partway through with a compressed onboarding timeline; first visible as the A3 data quality problem | Buyer | Cycle counts
[6 empty] | 16 | [5 empty] | General ledger
[6 empty] | 67 | [5 empty] | Exception log
Summary
Met
Partly met
Not met
For a Milestone, a negative variance means it happened early. For a Trajectory, read the variance with the direction of the metric: for cycle time, lower is better.
From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.

## Lessons
Audit Record: lessons, written as changes
Each lesson names what the next decision will do differently and where that change goes.
Lesson | Change to apply | Where it goes
Data migration quality has to be checked before a center goes live, not after | A pre-cutover data quality test becomes a standing assumption with its own check date | Next Decision Memo, assumptions
A center added mid-program cannot meet the same accuracy date as the others | A center added after commitment gets its own target and date, recorded as a change | Next Decision Memo, outcomes and changes table
From The Value Standard by Michael Brey. valuelattice.com/guides/. Licensed CC BY 4.0.