## Start Here
Purchase Outcome Register
Every significant commitment, tied to the financial statements a CFO and a board already read.
A working tool for the people who answer for results: the CFO who has been handed a target, the executive who owns a program, procurement, and the board that oversees them. Each row is one significant commitment, written by the person who will answer for it before money is committed. Each row names the line of the income statement or balance sheet it should move and is checked at dates named in advance. Rows roll up to the initiatives they serve and to the statements themselves.
What it is for
| Cost reduction | A cost target handed down from the board. Every purchase and program meant to deliver it, by line, with the gap between the plan and the target visible from day one.
| Revenue growth | Growth programs, with revenue counted only when the business owner who will answer for it confirms the claim. Vendor uplift models stay out.
| Risk reduction | Spending to reduce disruption, compliance or concentration risk, measured by the cost the risk actually creates today: expediting, stock-outs, penalties, write-offs.
| Capacity for growth | Investments that let the growth plan happen without new buildings or headcount, measured in capacity and in the capital spending they avoid.
| Working capital | Inventory, receivables and payables programs, measured as cash released on the balance sheet, with only holding costs reaching the income statement.
| M&A integration | Acquisition objectives and synergy targets, the combined baseline of both companies' statements, and a plain statement of whether each objective has been met.
| Board and renewal | A one-page summary for the board or executive committee, and a written record to open at every renewal.
How the sheets work together
| 1. Setup | Company, units, baseline statements, holding-cost rate, review threshold.
| 2. Initiatives | The targets handed down: what each must deliver, by when, measured on which statement.
| 3. Register | One row per commitment, linked to an initiative. Outcome, statement line, baseline, target, conditions, evidence, actuals.
| 4. Statement Bridge | Baseline statements, the effect committed, and the effect achieved, line by line.
| 5. M&A Alignment | Combines an acquired company's statements with yours, and states whether each acquisition objective has been met.
| 6. Board Summary | The one-page view: commitments, status, gaps, causes, and what it adds up to.
Five rules the workbook enforces
• The balance sheet and the income statement stay separate. Inventory released is cash; only the costs of holding it (storage, handling, insurance, obsolescence, and interest if debt-financed) reach the income statement. A flag appears when a row's income statement effect is larger than the holding-cost rate allows.
• Revenue is the business owner's claim. A revenue row counts toward results only when the owner has confirmed it; otherwise it is shown and excluded.
• Measure per unit where volume moves (cost per shipment, cases per agent), so growth or decline is not mistaken for savings or losses.
• Baselines come from your own records. Unconfirmed baselines are marked Provisional and flagged until confirmed.
• Status is computed, not chosen: reached, on track, behind (progress below the share of time elapsed, times the review threshold), missed, or not yet measured.
Legend
| Blue text | Enter or overwrite. Inputs only.
| Shaded | Calculated. Do not overwrite.
| Cream | Key assumptions on the Setup sheet.
The workbook opens with a worked example for a fictional distributor (amounts in $ thousands). Replace it with your own. Money is entered in the unit named on Setup.
From The Value Standard by Michael Brey. Licensed CC BY 4.0: edit it, put your own logo on it and use it commercially, and keep this attribution line so the next user can find the current copy at valuelattice.com/guides/.

## Setup
Setup
Company, units and the baseline statements every other sheet uses.
Company and units
Company | Fictional Distributor, Inc. | Shown on the Board Summary.
Fiscal year of the baseline | FY2025 | The year the baseline figures below come from.
Money unit | $ thousands | Enter every amount in the workbook in this unit.
As-of date | 2026-09-30 | The date of the latest check. Used for acquisition objectives.
Holding-cost rate for inventory | 12% | Storage, handling, insurance and obsolescence as a share of inventory value. Exclude the cost of capital; add interest only if inventory is debt-financed.
Review threshold | 75% | A commitment is Behind when its progress is below this share of the progress expected by now.
Use the combined M&A baseline? | No | Yes: the Statement Bridge uses the combined figures on M&A Alignment. No: it uses the baseline below.
Baseline statements (in the money unit above)
Statement line | Baseline | Source and notes
Revenue | 500000 | FY2025 audited income statement
Cost of goods sold | 380000
SG&A | 70000
R&D | 5000
Other operating expense | 10000
Operating income |  | Calculated
Inventory | 82000 | FY2025 year-end balance sheet
Accounts receivable | 61000
Accounts payable | 45000
Property, plant and equipment | 120000
Cash | 25000

## Initiatives
Initiatives
The targets handed down. Each commitment on the Register links to one of these.
THE TARGET (entered by the CFO or initiative owner) | [7 empty] | COVERAGE AND RESULTS (calculated from the Register)
ID | Initiative | Type | Executive sponsor | Measured on | Primary statement line | Target ($K) | Target date | Commit-ments | Committed at target | Plan coverage | Achieved to date | Achieved % of target | Behind or missed | Status
I-01 | Take $3.5M a year out of the cost to serve | Cost reduction | CFO | Income statement | Cost of goods sold | 3500 | 2026-12-31
I-02 | Release $10M of working capital | Working capital | CFO | Balance sheet | Inventory | 10000 | 2026-12-31
I-03 | Grow key-account revenue 5% | Revenue growth | Chief Revenue Officer | Income statement | Revenue | 10000 | 2026-12-31
I-04 | Halve the cost of single-source supply risk | Risk reduction | COO | Income statement | Cost of goods sold | 1200 | 2026-12-31
I-05 | Add capacity for the growth plan without a new building | Capacity for growth | COO | Balance sheet | Property, plant and equipment | 8000 | 2027-06-30
I-06 | Deliver the acquisition's SG&A synergies | M&A integration | CFO | Income statement | SG&A | 2500 | 2027-03-31
Target ($K): for an income statement initiative, the favorable annual effect on profit; for a balance sheet initiative, the cash released (or capital spending avoided). Plan coverage compares what the linked commitments promise with the target; a Plan gap means the plan does not yet add up to the target, before anything has gone wrong.

## Register
Register
One row per significant commitment: written before signing, checked at the dates it names.
THE COMMITMENT | [6 empty] | THE MEASURE | [7 empty] | CONDITIONS AND EVIDENCE |  |  | TRACKING | [5 empty] | FINANCIAL EFFECT ($K)
ID | Initia-tive | Commitment | Type | Vendor or counterparty | Business owner | What it has to produce (owner's words) | Statement | Statement line | Metric and unit | Baseline | Baseline status | Baseline date | Target | Target date | Conditions on our side | Vendor's part | Evidence that will count | Latest actual | Last checked | Progress | Expected by now | Status | If behind or missed: whose condition | Revenue confirmed by owner | Favorable income statement effect at target ($K/yr) | Income statement effect achieved ($K/yr) | Cash released at target ($K) | Cash released achieved ($K) | Flags
P-01 | I-02 | Demand planning system | Purchase | (vendor) | VP Supply Chain | Carry less stock without hurting fill rate | Balance sheet | Inventory | Average inventory ($K) | 82000 | Confirmed | 2025-12-31 | 74000 | 2026-12-31 | Planners adopt the new forecast; item master cleaned before go-live | Forecast engine live by Q2; weekly accuracy report on our SKUs | Our month-end inventory, not a vendor dashboard | 77500 | 2026-09-30 | [5 empty] | 960 |  | 8000
P-02 | I-01 | Transportation management system | Purchase | (vendor) | Director, Logistics | Lower freight cost per shipment at today's service level | Income statement | Cost of goods sold | Freight $ per shipment | 118 | Confirmed | 2025-12-31 | 111 | 2026-06-30 | Carrier rate data loaded before go-live | Rate shopping and load building live on all lanes | Freight invoices divided by shipments, from our ledger | 117 | 2026-09-30 |  |  |  | Our side |  | 2800
P-03 | I-01 | Customer service platform | Purchase | (vendor) | VP Customer Service | Handle 10% more cases with the same team | Income statement | SG&A | Cases a year handled by 48 agents | 120000 | Provisional | 2025-12-31 | 132000 | 2026-03-31 | Knowledge base migrated; agents trained before cutover | Case routing and self-service live | Case counts from our system; headcount from HR | 133000 | 2026-03-31 | [5 empty] | 336
P-04 | I-03 | Key-account pricing analytics | Purchase | (vendor) | VP Sales | Lift key-account revenue 5% at today's discount levels | Income statement | Revenue | Key-account revenue ($K) | 200000 | Confirmed | 2025-12-31 | 210000 | 2026-12-31 | Account teams use the price guidance in every quote | Price guidance live in the quoting tool | Invoiced revenue for the named accounts | 204000 | 2026-09-30 |  |  |  | Not yet known | Yes | 10000
P-05 | I-04 | Dual-source supply agreement | Renewal | (supplier) | Director, Procurement | Cut expediting and stock-out costs on single-source parts in half | Income statement | Cost of goods sold | Expediting and stock-out cost ($K a year) | 2400 | Confirmed | 2025-12-31 | 1200 | 2026-12-31 | Second source qualified by engineering by Q1 | Second source shipping at agreed lead times | Expedite charges and lost-order log | 1700 | 2026-09-30 | [5 empty] | 1200
P-06 | I-05 | Warehouse automation | Purchase | (vendor) | VP Operations | Ship 20% more orders a day from the existing building, avoiding the $8M expansion in the plan | Balance sheet | Property, plant and equipment | Orders shipped a day | 10000 | Confirmed | 2025-12-31 | 12000 | 2027-06-30 | Slotting redesign done; overtime rules agreed | Robots and software at rated throughput | Daily shipped-order counts from our WMS | 10600 | 2026-09-30 |  |  |  | Vendor's side |  |  |  | 8000
P-07 | I-06 | ERP consolidation of the acquired company | Acquisition integration | (vendor) | CFO | Run the acquired company on our ERP and close its separate finance and IT cost | Income statement | SG&A | Annual finance and IT cost of the acquired company ($K) | 3100 | Confirmed | 2026-03-31 | 1600 | 2027-03-31 | Chart of accounts mapped; data cleansed before cutover | Cutover by Q1 FY27; parallel run of one close | General ledger cost centers for the acquired company | 2900 | 2026-09-30 |  |  |  | Our side |  | 1500
Note on Z7: Holding costs on the $8.0M inventory reduction at the 12% rate on Setup. The $8.0M itself is cash released, not profit.
Note on K9: Provisional: confirm at the first post-go-live check.
Note on Z10: Revenue increase. Counts toward results only because the VP Sales has confirmed it (column Y). The Statement Bridge adds the matching cost of sales.
Note on AB12: Capital spending avoided against the growth plan (no new building), so cash released versus plan.

## Statement Bridge
Statement Bridge
Baseline statements, the effect committed and the effect achieved, line by line ($K).
Statement line | Statement | Baseline | Favorable effect at target | Pro forma at target | Favorable effect achieved | Pro forma achieved | Target effect as % of line
Income statement
Revenue | Income statement
Cost of goods sold | Income statement
SG&A | Income statement
R&D | Income statement
Other operating expense | Income statement
Operating income
Balance sheet
Inventory | Balance sheet
Accounts receivable | Balance sheet
Accounts payable | Balance sheet
Property, plant and equipment | Balance sheet
Cash | Balance sheet
Favorable effect: profit improvement on income statement lines; cash released on balance sheet lines. Pro forma applies each effect in the right direction (costs and assets go down, revenue, payables and cash go up).
Other operating expense includes the holding-cost effect of balance sheet rows (inventory). Cost of goods sold adds the cost of sales that goes with any confirmed revenue increase, at the baseline cost-of-sales ratio.
Revenue rows the business owner has not confirmed are shown at target but count zero toward the achieved column. Capital spending avoided (property, plant and equipment) is measured against the plan, not the baseline.

## M&A Alignment
M&A Alignment
Combine an acquired company's statements with yours, and state plainly whether each acquisition objective has been met.
A. Combined baseline ($K)
Statement line | Acquirer (from Setup) | Acquired company | Adjustments and eliminations | Combined baseline | Notes
Revenue |  | 60000 | -2000 |  | Intercompany sales eliminated
Cost of goods sold |  | 46000 | -2000 |  | Intercompany purchases eliminated
SG&A |  | 9500 | 0
R&D |  | 0 | 0
Other operating expense |  | 1200 | 0
Inventory |  | 11000 | 0
Accounts receivable |  | 7500 | -300 |  | Intercompany balances
Accounts payable |  | 5200 | -300 |  | Intercompany balances
Property, plant and equipment |  | 14000 | 0
Cash |  | 3000 | 0
To run every sheet on the combined figures, set "Use the combined M&A baseline?" to Yes on Setup. Green figures link to Setup.
B. Acquisition objectives and whether they have been met
Key objective, as stated at acquisition | Linked initiative | Target ($K) | Target date | Achieved to date ($K) | Achieved % | Statement of whether met
Deliver $2.5M a year of SG&A synergies by the end of FY27 Q1 | I-06 | 2500 | 2027-03-31
Hold the acquired company's inventory turns at or above ours
The statement of whether each objective has been met is the line accounting standard setters have proposed requiring for significant acquisitions. Keeping it here costs one formula.

## Board Summary
Board Summary
Significant commitments, what they are for, and what they add up to.
| Significant commitments | Reached their stated result |  | Behind or missed |  | Initiatives with a plan gap
| Operating income, achieved ($K/yr) | Operating income, at target ($K/yr) |  | Cash released to date ($K) |  | Cash released at target ($K)
By initiative
| Initiative | Measured on | Target ($K) | Committed | Achieved | Coverage | Status | Target | Committed | Achieved
Behind or missed: whose condition failed
Our side
Vendor's side
Both
Not yet known
Results count only measured progress, capped at each target. Revenue counts only where the business owner has confirmed the claim. Profit and cash are kept apart throughout.

## Lists (hidden)
Statement line | Statement | Sign | Statement | Initiative type | Commitment type | Baseline status | Side | Yes/No | Direction
Revenue | Income statement | 1 | Income statement | Cost reduction | Purchase | Confirmed | Our side | Yes | Decrease
Cost of goods sold | Income statement | -1 | Balance sheet | Revenue growth | Renewal | Provisional | Vendor's side | No | Increase
SG&A | Income statement | -1 |  | Risk reduction | Internal program |  | Both
R&D | Income statement | -1 |  | Capacity for growth | Acquisition integration |  | Not yet known
Other operating expense | Income statement | -1 |  | Working capital
Inventory | Balance sheet | -1 |  | M&A integration
Accounts receivable | Balance sheet | -1
Accounts payable | Balance sheet | 1
Property, plant and equipment | Balance sheet | -1
Cash | Balance sheet | 1